## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | US_1_Role Selection
Task_1 | Initial Role Selection jsp |  | Jishnu | Completed | 1 |  | 1
Task_2 | Feedback Model |  | Jishnu | Completed | 0.5 | 0.5
Task_3 | Secret Question Model |  | Shabeer | Completed | 0.5 | 0.5
Task_4 | Secret questionare Model |  | Linjo | Completed | 0.5 | 0.5
Task_5 | Role Selection StyleSheet |  | Jishnu | Completed | 1.5 |  | 1.5
Task_6 | Role Selection Controller |  | Shabeer | Completed | 1 |  | 1
User Story #2 | US_2_User Registration and Login
Task_1 | User Registration form |  | Anusha | Completed | 1 |  | 1.5
Task_2 | Reg Form Stylesheet |  | Sai Vamshi | Completed | 1.5 |  | 1.5
| Analyst Reg form |  | Jishnu | Completed | 1.5 |  | 1.5
Task_3 | Creating database |  | Anusha | Completed | 2 | 2.5
Task_4 | Create Model Class |  | Linjo | Completed | 1 | 0.5
Task_5 | Create Validator class |  | Linjo | Completed | 1 |  | 1
Task_6 | Submission Confirmation Page |  | Linjo | Completed | 0.75 |  | 1
Task_7 | Admin Model clas |  | Shabeer | Completed | 0.5 | 0.5
Task_8 | Analyst Model Class |  | Anusha | Completed | 0.5 | 0.5
Task_9 | Complaint Model |  | Linjo | Completed | 0.5 | 0.5
User Story #3 | US_3_User Registration and Login
Task_1 | User Login jsp |  | Shabeer | Completed | 1 |  | 1
Task_2 | Login css |  | Shabeer | Pending | 0.5
Task_3 | Reg Controller |  | Shabeer | Completed | 2 |  | 2
Task_4 | Login controller |  | Linjo | Completed | 1 |  | 1
Task_5 | User Repository |  | Linjo | Completed | 0.5 |  | 0.5
Task_6 | Analyst Repository |  | Linjo | Completed | 0.5 |  | 0.5
Task_7 | UserService |  | Jishnu | Completed | 1 |  | 1
User Story #6 | US_6_Admin Registration and Login
Task_1 | admin Login controller |  | Linjo | Completed | 1 |  | 1
Task_2 | admin sql table |  | Anusha | Completed | 1 | 1
Task_3 | All Model Class made To Entity |  | Linjo | Completed | 1.5 |  | 1.5
Task_4 | Test Methods |  | Jishnu | Completed | 1 |  | 1
Task_5 | UserService |  | Shabeer | Pending | 1
User Story #7 | US_7_User Authentication
Task_1 | admin login jsp |  | Shabeer | Completed | 1 |  | 1
Task_2 | admin login css |  | Sai Vamshi | Completed | 1.5
User Story #8 | US_8_Complaint creation page
Task_1 | conplaint creation jsp |  | Sai Vamshi | Pending | 1
Task_2 | complaint creation css |  | Anusha | Pending | 0.5
Task_3 | usercontroller-complaint methods |  | Shabeer | Pending | 1.5
Task_4 | complaint creation table |  | Jishnu | Pending | 1
Task_5 | complaint validation method |  | Linjo | Pending | 1
User Story #9 | US_11_Complaint notification
Task_1 | complaint successful jsp |  | Anusha | Pending | 1
Task_2 | complaint successful css |  | Sai Vamshi | Pending | 1
Task_3 | complaint list page |  | Shabeer | Pending | 1.5
Task_4 | complaint list page css |  | Jishnu | Pending | 1.5
Task_5 | controller add methods |  | Linjo | Pending | 1
User Story #10 | US_10_Complaint assignment
Task_1 | Complaint view admin |  | Linjo | Pending | 1
Task_2 | complaint form in view page |  | Linjo | Pending | 1
Task_3 | Complaint view admin css |  | Sai Vamshi | Pending | 1
TOTAL |  |  |  |  | 43.75 | 7 | 20.5 | 0 | 0 | 0

## Sprint -2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #11 | US_11_Complaint list
Task_1 | filter in complaijnt list page |  | Jishnu | Pending | 1
Task_2 | filter in complaijnt list page css |  | Shabeer | Pending | 1
Task_3 | filter in complaint dao |  | Anusha | Pending | 0.5
Task_4 | filter in complaint daoImpl |  | Anusha | Pending | 1
Task_5 | filter in complaint daoService |  | Linjo | Pending | 0.5
Task_6 | download option |  | Sai Vamshi | Pending | 2
Task_7 | pagenation |  | Linjo | Pending | 1.5
User Story #12 | US_12_Complaint Acknowledgement
Task_1 | support analyst login |  | Jishnu | Pending | 1
Task_2 | support analyst login css |  | Sai Vamshi | Pending | 1
Task_3 | analyst controller |  | Linjo | Pending | 1
Task_4 | complaint assigned analyst jsp |  | Linjo | Pending | 1
Task_5 | complaint assigned css |  | Anusha | Pending | 1
Task_6 | support analyst table |  | Shabeer | Pending | 0.75
User Story #13 | US_13_Complaint Transfer
Task_1 | email |  | Linjo | Pending | 2
Task_2 | complaint assigned jsp - include level change |  | Shabeer | Pending | 1
Task_3 | complaint assigned jsp - include level change css |  | Anusha | Pending | 1
Task_4 | controller |  | Jishnu | Pending | 1.5
User Story #14 | US_14_Search Complaint
Task_1 | conplaint list - search new jsp |  | Jishnu | Pending | 1
Task_2 | conplaint list - search new jsp css |  | Sai Vamshi | Pending | 1
Task_3 | complaint dao - new method |  | Linjo | Pending | 1.5
Task_4 | controller search list |  | Shabeer | Pending | 1
User Story #15 | US_15_Closing a Complaint
Task_1 | email to user |  | Linjo | Pending | 2
Task_2 | complaint assigned jsp - analyst |  | Anusha | Pending | 1.5
Task_3 | complaint assigned jsp - analyst css |  | Jishnu | Pending | 1.5
Task_4 | controller |  | Sai Vamshi | Pending | 1.5
Task_5 | add change status in user complaint creation jsp |  | Shabeer | Pending | 1
User Story #16 | US_16_Re-Opening Complaint
Task_1 | email to analyst/admin |  | Linjo | Pending | 2
Task_2 | controller |  | Shabeer | Pending | 1
User Story #17 | US_17_Review Questionnaire
Task_1 | feedback creation jsp admin |  | Sai Vamshi | Pending | 1
Task_2 | feedback creation jsp admin css |  | Sai Vamshi | Pending | 1
Task_3 | controller questionare |  | Jishnu | Pending | 2
Task_4 | Questionare table |  | Linjo | Pending | 1
Task_5 | feedback submit jsp user |  | Anusha | Pending | 1
Task_6 | feedback submit jsp user css |  | Anusha | Pending | 1
Task_7 | controller feedback submit |  | Jishnu | Pending | 1
Task_8 | Qsn and Answers table |  | Linjo | Pending | 1
Task_9 | dao methods add |  | Shabeer | Pending | 1.5
User Story #18 | US_18_Write review
Task_1 | email to user to review the feedback |  | Shabeer | Pending | 1.5
Task_2 | controller - 2 methods |  | Anusha | Pending | 1.5
Task_3 | complaint dao add methods |  | Linjo | Pending | 1.5
User Story #20 | US_20_Other validations
Task_1 | pass recovery qsns |  | Sai Vamshi | Pending | 1
Task_2 | pass recovery |  | Sai Vamshi | Pending | 1
Task_3 | pass recovery css |  | Sai Vamshi | Pending | 1
Task_4 | pass recovery controller |  | Anusha | Pending | 1
Task_5 | id recovery |  | Shabeer | Pending | 1
Task_6 | id recovery css |  | Shabeer | Pending | 1
Task_7 | id recovery controller |  | Shabeer | Pending | 1
Task_8 | id display |  | Jishnu | Pending | 1
Task_9 | table secret qsn and answers |  | Jishnu | Pending | 1
Task_10 | registration jsp add secret qsns |  | Jishnu | Pending | 1
User Story #21
Task_1 | dao security qsn interface |  | Linjo | Pending | 1
Task_2 | dao security qsn impl |  | Linjo | Pending | 1
Task_3 | dao security qsn service |  | Linjo | Pending | 1
Task_4 | login page - add "forgot" links |  | Anusha | Pending | 1
Task_5 | logoff to all jsps |  | Anusha | Pending | 1
Task_6 | controller |  | Anusha | Pending | 1
TOTAL |  |  |  |  | 64.75 | 0 | 0 | 0 | 0 | 0

## Sprint -3
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task_1
Task_2
Task_3
Task_4
User Story #2
Task_1
Task_2
Task_3
Task_4
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A