## Cover Page
Online Customer Care and Service Center
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Jayagandhan
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Online Customer Care and Service Center Project ID: A073 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Priorities | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Role Selection | User/Support Analyst/Admin | Ability of the system to allow a user to choose the required User role for registration | 1. When a visitor opens the web page, the initial screen should display the options to select from the different roles to which a user would like to register. 2. The roles to be displayed as User/Support Analyst/Admin
US_2 | User Registration and Login | User, Support Analyst | Ability of the system to procure the fundamental details of the User, save the user details in the Database and allow user login | 1. When the user clicks on the registration, it should re-direct to registration form Role selection - User/ support analyst should be present 2. User needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name, Designation - Should be selected from drop down Contact Number -should be of 10 digits User Id/Analyst id - Autogenerated Password - should be of minimum 6 letters with special characters included. DOB - age should not be less than 18. Gender - Drop down/checkbox/radiobutton Support Level (L1,L2,L3) - only for Analyst, L1, L2, L3 should be listed in drop down etc. 3. Clicking ‘Submit’ should validate the datatype constraints for each field Note - Trainees can add/neglect fields that will be appropriate and validations should be handled for all fields 4. User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5. Post-successful field level validation, save the information in the database 6. Upon saving the information in the database, display the message, ‘Your details are submitted successfully’.
US_3 | User Authentication | User | Ability of the system to authenticate the credentials of the registered User | 1. A registered user – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. 2. A user whose registration is rejected – is unable to login and get the credentials authenticated, the user is presented with relevant error messages: Invalid User ID (or) Incorrect Password
US_6 | Admin Registration and Login | Admin | Ability of the system to procure the fundamental details of the Admin, save the user details in the Database and allow user login | 1-Users should have option to select their role option 2-Admin should select the Admin option. 3-Admin's User id and password should be pre-loaded in the database, which can be used to log in.
US_7 | User Authentication | Admin | Ability of the system to authenticate the credentials of the registered Admin | 1. A registered user – is able to click ‘Login’ link, after keying in ‘User ID’ & ‘Password’ field and get his credentials authenticated with the existing database entry. 2. A user whose registration is rejected – is unable to login and get the credentials authenticated, the user is presented with relevant error messages: Invalid User ID (or) Incorrect Password
US_8 | Complaint creation page | User | Ability of the system to allow user to create Complaint | 1. User on successful login should land up in Complaint creation page 2. Complaint creation page should have category to select the type of Complaint to be raised 3. On selecting the category, user should be able to enter the problem statement 4. User details, such as User id, mobile number etc should be populated in the respective field taken from the database, as updated during the registration . User should be able to change the contact number if required - but this should not change the contact number that is saved during registration. 5- The changed mobile number should be used only for this Complaint prupose. 6. System generated Complaint number should be created for the Complaint user is creating. 7. On clicking submit, data validation and mandatory field validation shloud be done and prompted with appropriate messages
US_9 | Complaint notification | Admin | Complaint details to be viewed by Admin | 1. On successful submission of a Complaint, somplain sucessfully submitted should be displayed 2. Admin should be able to view the complaint details in the complaint list page.
US_10 | Complaint assignment | Admin | Ability of the system to allow admin to assign Complaint | 1. Admin can self assign/assign the Complaint to the team based on the Level of issue. 2. Admin should be able to change the category of the Complaint if he feels it is incorrect. 3. On successful assignment, admin should be able to change the status of the Complaint (can be open, wip, closed,reopen etc) - to be selected from the drop down. Note - Use drop downs, radio buttons, Check boxes wherever applicable.
US_11 | Complaint list | Admin | Ability of the system to allow admin to view/Modify Complaint list | 1. Admin lands on Complaint list page on login where all the Complaints are listed 2. Admin should be able to filter based on date/category/admin id/ etc 3. Admin should be able to sort based on date/category/admin id/ etc 4. Admin on selecting the required Complaint, the Complaint details page gets selected 5. Admin should be able to download the displayed report to excel or pdf Note - Use pagenation while listing
US_12 | Complaint Acknowledgement | Support Analyst | Ability of the system to allow show the assigned Complaints and view/modify details | 1. On Login, Support Analyst should be able to view the Complaints assigned to him 2. On slecting any one complaint, the analyst should be able to view the details logged in by the user 3. Support Analyst should be able to update the status of the Complaint
US_13 | Complaint Transfer | Support Analyst | Ability of the system to allow Support Analyst to escalate the Complaint to higher levels | 1. Support Analyst should be able to transfer/escalate a Complaint to next level if required. 2. Once Complaint is re-assigned to the next level team, an email to be triggerred to the new analyst with the Complaint details 3. The new analyst to be allowed to view/update the Complaints assigned
US_14 | Search Complaint | User | Ability of the system to allow searching/sorting Complaint details | 1. Complaint creation page should have Search option 2. Searching should direct to Complaint list page 3. Searching should have option to search based on Complaint id, category, Complaint raiser id, date 4. On entering the appropriate details, search list should be displayed
US_15 | Closing a Complaint | Support Analyst/Admin | Ability of the system to allow the admin and user to close the Complaint status. | 1. Admin/Support Analyst on successfully resolving the issue, should update the status as closed 2. Admin/Support Analyst Upon closing mail should be triggered to user who raised the Complaint, giving option to reopen/close the Complaint from their end
US_16 | Re-Opening Complaint | User | Ability of the system to allow the user to re-open the Complaint if required | 1. Once the Complaint has been resolved by the support analyst, the User should be able to Close/Re-open the Complaint from their end. 2. Upon reopen, mail should be sent to admin/Support Analyst who worked on the issue to bring the issue to closure 4. Upon Closing, the Complaint should be closed.
US_17 | Review Questionnaire | Admin | Ability of the system to allow admin to create review questionnaire for the User | 1. Admin should be able to create review questionnaire for the User to provide feedback on the services. 2. The user should also be able to provide any improvement suggestions
US_18 | Write review | User | Ability of the system to allow the user to review the Complaint service | 1. User on closing the Complaint, should be sent an email notification to answer the review questionnaire on the service provided.
US_20 | Other validations | Admin/Support Analyst/User | Ability of the system to allow add on validations like Forgot Customer ID, Forgot Password | 1. During registration, System should pop up three secret questions for Password recovery. 2. When the user clicks Forgot User ID, system should ask for the secret questions. On answering the questions correctly, the User ID should be displayed. Secret questions' answer should have been already stored in the system while registration itself. 3. When the user clicks Forgot Password, system should ask for the User ID and secret questions, registered mobile number, registered Email id. On answering the questions correctly, the password reset page should be displayed. 4. On entering the details in the password reset page, password should be validated 5. On clicking Submit, the details should be saved to the Database
US_21 | User logoff | Admin/Support Analyst/User | Ability of the system to allow the user to logoff | 1. Option to log off from the system.

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000